## Usage Guidelines
Area | Issue Tracker Usage Guidelines
General maintenance | The issue tracker spreadsheet is to be created by the person sending the document or work product out for review. Reviewers/Respondents need to update the Issue Tracker spreadsheet with their review comments/suggestions and update the Review Status appropriately.
Item | The item number is manually generated to allow for the item number to easily be referenced in notes, even if the item itself is moved to another position or sheet. The item number must not be changed when updating the tracker.
Date Opened | Date issue was communicated to owner
Status | The current conditon of the item - Open - Item noted. Further investigation or work needed. - Deferred - Further action deferred until Target indicated - Future - The item is not feasible right now, although potentially desirable. It is put on a wish list for future investigation at an unspecified target. - Closed - Item has been resolved. - Waiting - Waiting upon further clarification or action, as specified in the notes.
Section or Reference | An identifying reference to the core issue. This may be - a section number in a document - a reference to a file, routine, and/or line numbers - other reference, as fits the collateral being reviewed
Description | Statements describing the issue
Submitter | The person who raised the issue.
Owner | The person responsible for action to address the issue.
Type | The Type column indicates the type of response made. These include: - Change - A change was made as per the issue description or the note. - Note - The issue was noted. - Clarification - More information is needed. - Duplicate - The issue was previously noted. (Reference the item number in the duplicate item.) - No Change - No change
Target | Target date, time frame, or category of action to revisit, address, or close the issue
Notes | These include the responses to the issue. The note must always include the date of the last update on the issue and the name of the person making the update. When updating the spreadsheet, color the last set of changes red. This makes it easy to for a reviewer or key stakeholder to find the latest changes. Prior to updating, all previous changes must be turned black. It is left to the reviewer to identify what constitutes an update. A loose guideline is that any set of comments coming in over a short period of a few days is an update. When responding to issues, a loose guideline is that any update that has not been published in the previous 10 days is an update.
Resolution | The outcome of the issue

## Review Comments
Item | Date Opened | Status (Open, Deferred, Future, Closed, or Waiting) | Section or Reference | Description | Submitter | Owner | Type (Change, Note, Clarification, Duplicate or No Change) | Target | Notes | Resolution
1 | 2019-06-19 |  | Generic | 1. Generic - PVRST to be replaced with PVST | Praveen Hoskote Madhusudhana | Chaitanya Arava | Change |  | Replaced PVRST with PVST.
2 | 2019-06-19 |  | ft_pvst_portchannel_cost_member_remove_add | 2. Tc - Verify topology changes when there is a Change in the cost of a port-channel interface by removing channel-members with PVST configured. Adding/Deleting members will not change cost. Please refer requirement 7 in FS. "7. Port channel path cost will be same as the member port cost, it will not be cumulative of member ports cost" | Praveen Hoskote Madhusudhana | Chaitanya Arava | Chnage |  | Updated TC description expected result that port-channel cost does not change on adding/removing members.
3 | 2019-06-19 |  | ft_pvst_portchannel_member_remove_default_vlan | 3. TC - "Verify that with PVST configured, member port removed from lag interface will become part of default vlan instance." Port removed will not be part of default VLAN. Also description on this TC is not very clear. | Praveen Hoskote Madhusudhana | Chaitanya Arava | Change |  | There is no default vlan in SONiC. Removing member port from port-channel will not place the physical port in default VLAN. This TC is not applicable so removing from testplan.
4 | 2019-06-19 |  | ft_pvst_udld | 4. TC - "Verify the PVST is converging fine when UDLD is enabled." UDLD is not supported | Praveen Hoskote Madhusudhana | Chaitanya Arava | Change |  | Removed UDLD TC from testplan.
5 | 2019-06-19 |  | ft_pvst_l3_traffic | 5. Row 39 - No summary of TC | Praveen Hoskote Madhusudhana | Chaitanya Arava | Change |  | Added Summary to TC ft_pvst_l3_traffic
6 | 2019-06-19 |  | ft_pvst_l3_traffic | 6. Row 39 - OSPF is not supported | Praveen Hoskote Madhusudhana | Chaitanya Arava | Change |  | Updated TC ft_pvst_l3_traffic to configure BGP.
7 | 2019-06-19 |  | RESTCONF,REST API TCs | 7. Row 72 to 77 - REST is not supported in Arlo | Praveen Hoskote Madhusudhana | Chaitanya Arava | Change |  | Removed Arlo unsupported RESTCONF,REST API TCs from testplan.
8 | 2019-06-25 |  | ft_pvst_l2acl_deny_ieeebpdu ft_pvst_l2acl_deny_sstpbpdu | On TC - Verify L2-ACL configured to deny IEEE STP BPDU – I checked with SAI team on this and in current SONiC implementation control packet traps have higher priority so applying deny ACL will not have any impact. | Sandeep Kulambi | Chaitanya Arava | Change |  | As per review comments, deny of BPDUs will not have any impact. Removed TCs "ft_pvst_l2acl_deny_ieeebpdu and ft_pvst_l2acl_deny_sstpbpdu" from testplan
9 | 2019-06-25 |  | ft_pvst_pvid_inconsistency | On TC - Verify that Switch goes toPVID inconsistent state when different native VLANs are configured with PVST enabled – This is not supported currently I investigated this and it may not be possible to support this, as in XGS untagged BPDU received in ASIC are converted to tagged packets and sent to CPU. So when its received by STP it will not be able to distinguish whether the original packet received was tagged or untagged. | Sandeep Kulambi | Chaitanya Arava | Change |  | As per review comments,this test scenario is not supported so removed TC ft_pvst_pvid_inconsistency from testplan.

## Reviewers
[5 empty] | Open | In Progress | Review Complete | Approved
Reviewers
| Area | Reviewer | Review Status | Date Reviewed
| Any developers owning components which interact with or are directly affected by this feature/change, including, but not limited to the following areas: User Interface, Application, Driver for affected or lead platform) | Narendra Bandarupalli | Open
| Customer Operations / Support | Ramakrishna Dronamraju Venkatavalli | Open
| Quality Assurance | Giri Babu Sajja | Open
|  | Anil Kumar Kolkaleti | Open
The possible values(and their meaning) of "Review Status" cell would be:
- Open (Review assigned to reviewer) - this state will be assigned by the author
- In Progress (Document under review, comments given/under discussion) – this state will be changed by the reviewer
- Review Complete (All the comments have been incorporated) - this state will be changed by the author once all the comments have been incorporated
- Approved (Reviewer approves the document) - this state will be changed by the reviewer to approve the document if all the comments have been taken care of OR the status can be moved back to In Progress state.
General Guidelines:
:- Document Author update the Reviewers list (Set the Review Status to Open)
:- Reviewers update the Issue Tracker document with their review comments/suggestions (Change the Review Status to In Progress)
:- Document Author updates the Issue Tracker with responses to comments and updates the document, if required (Change the Review Status to Review Complete)
:- Once all the comments from a reviewer are addressed, the reviewer can then update the Review status against his/her name. (Change the Review Status to Approved)