## Usage Guidelines
Area | Issue Tracker Usage Guidelines
General maintenance | The issue tracker spreadsheet is to be created by the person sending the document or work product out for review. Reviewers/Respondents need to update the Issue Tracker spreadsheet with their review comments/suggestions and update the Review Status appropriately.
Item | The item number is manually generated to allow for the item number to easily be referenced in notes, even if the item itself is moved to another position or sheet. The item number must not be changed when updating the tracker.
Date Opened | Date issue was communicated to owner
Status | The current conditon of the item - Open - Item noted. Further investigation or work needed. - Deferred - Further action deferred until Target indicated - Future - The item is not feasible right now, although potentially desirable. It is put on a wish list for future investigation at an unspecified target. - Closed - Item has been resolved. - Waiting - Waiting upon further clarification or action, as specified in the notes.
Section or Reference | An identifying reference to the core issue. This may be - a section number in a document - a reference to a file, routine, and/or line numbers - other reference, as fits the collateral being reviewed
Description | Statements describing the issue
Submitter | The person who raised the issue.
Owner | The person responsible for action to address the issue.
Type | The Type column indicates the type of response made. These include: - Change - A change was made as per the issue description or the note. - Note - The issue was noted. - Clarification - More information is needed. - Duplicate - The issue was previously noted. (Reference the item number in the duplicate item.) - No Change - No change
Target | Target date, time frame, or category of action to revisit, address, or close the issue
Notes | These include the responses to the issue. The note must always include the date of the last update on the issue and the name of the person making the update. When updating the spreadsheet, color the last set of changes red. This makes it easy to for a reviewer or key stakeholder to find the latest changes. Prior to updating, all previous changes must be turned black. It is left to the reviewer to identify what constitutes an update. A loose guideline is that any set of comments coming in over a short period of a few days is an update. When responding to issues, a loose guideline is that any update that has not been published in the previous 10 days is an update.
Resolution | The outcome of the issue

## Review Comments
Item | Date Opened | Status (Open, Deferred, Future, Closed, or Waiting) | Section or Reference | Description | Submitter | Owner | Type (Change, Note, Clarification, Duplicate or No Change) | Target | Notes | Resolution

## Reviewers
[5 empty] | Open | In Progress | Review Complete | Approved
Reviewers
| Area | Reviewer | Review Status | Date Reviewed
| Any developers owning components which interact with or are directly affected by this feature/change, including, but not limited to the following areas: User Interface, Application, Driver for affected or lead platform) | Sachin Suman Shirisha Dasari Naveen Kumar Aketi | Open
| Customer Operations / Support | Ramakrishna Dronamraju Venkatavalli | Open
| Quality Assurance | Giri Babu Sajja | Open
|  | Anil Kumar Kolkaleti | Open
|  | Chaitanya Kumar Vella | Open
|  | Prudvi Mangadu | Open
The possible values(and their meaning) of "Review Status" cell would be:
- Open (Review assigned to reviewer) - this state will be assigned by the author
- In Progress (Document under review, comments given/under discussion) – this state will be changed by the reviewer
- Review Complete (All the comments have been incorporated) - this state will be changed by the author once all the comments have been incorporated
- Approved (Reviewer approves the document) - this state will be changed by the reviewer to approve the document if all the comments have been taken care of OR the status can be moved back to In Progress state.
General Guidelines:
:- Document Author update the Reviewers list (Set the Review Status to Open)
:- Reviewers update the Issue Tracker document with their review comments/suggestions (Change the Review Status to In Progress)
:- Document Author updates the Issue Tracker with responses to comments and updates the document, if required (Change the Review Status to Review Complete)
:- Once all the comments from a reviewer are addressed, the reviewer can then update the Review status against his/her name. (Change the Review Status to Approved)